Task Group (TG) — 2026 Meeting Schedule & Agendas

Chair: J. Ianelli  |  All meetings: Online (Zoom/Teams)  |  14:00–15:30 CET

08:00–9:30 Lima (PET) 09:00-10:30 Santiago (CLT)

At-a-Glance Schedule

| Meeting | Date | Topic | Key Milestone |
| --- | --- | --- | --- |
| TG-01 | Thu 26 March 2026 | Post-Commission Kickoff | — |
| TG-02 | Thu 9 April 2026 | WP1 Launch & Benchmark Preparation | → Leads to: Benchmark Workshop, Lima (May) |
| TG-03 | Thu 30 April 2026 | Final Pre-Benchmark Preparation | → Leads to: Benchmark Workshop, Lima (~12–16 May) |
| TG-04 | Thu 28 May 2026 | Post-Lima / Pre-Intersessional Debrief | → Leads to: MSE-02 draft performance metrics |
| TG-05 | Thu 11 June 2026 | Pre-Wageningen Final Preparation | → Leads to: MSE Workshop, Wageningen, 15–19 June 2026 |
| TG-06 | Thu 9 July 2026 | Post-Wageningen: CMP Shortlist Review | → SC14 paper drafting begins |
| TG-07 | Thu 13 August 2026 | Pre-SC14 Draft Review | → Leads to: SC14 (September 2026) |
| TG-08 | Fri 28 August 2026 | Final SC14 Paper Sign-off | → SC14 submission deadline |
| TG-09 | Thu 8 October 2026 | Post-SC14 Debrief & Commission Prep | → Leads to: Commission decision (Nov/Dec 2026) |
| TG-10 | Thu 12 November 2026 | WP4 Report Review & Year-End Close | → SC15 / archive |

Regular = 2nd Thursday of month.  Extra = milestone-driven additional call.

2026 Programme Milestones (for reference)

| Month | Event | Deliverable | Output for |
| --- | --- | --- | --- |
| May 2026 | Benchmark Workshop — Lima (Peru) | Candidate assessment models | SC Intersessional |
| Late May 2026 | SC Intersessional meeting | Approved OM for MSE | Wageningen workshop |
| Jun 15–19 | MSE Workshop — Wageningen (WMR/NL) | CMP shortlist | SC14 document |
| Sep 2026 | SC14 — Scientific Committee | CMP recommendation | Commission decision |
| Nov 2026 | WP4 final deliverable | Technical report + source code | SC15 / archive |

SPRFMO Jack Mackerel MSE — Technical Group (TG) Session Agenda Plan 2026

Five 2-hour TG sessions (March–June 2026) leading to the Lima Benchmark (early May) and the Wageningen MSE Workshop (16 June). Each session covers topics for discussion and decisions; where consensus cannot be reached, the decision is deferred one session. Based on Carruthers et al. (2024) MSE roadmap phases.

Colour legend:  White = discussion topics    Yellow = items requiring decision    Grey = pre-meeting preparation    Blue = linked working papers

| TG | Date | Main Topics for Discussion | Topics Requiring Decision | Pre-meeting Prep | WPs |
| --- | --- | --- | --- | --- | --- |
| TG-01 — 26 Mar 2026 15:00 CET |  |  |  |  |  |
| 1 | 26 Mar 2026 15:00 CET | - Review & endorse working paper plan (10 WPs: Benchmark, Wageningen, SC14) - Sequence and allocation of technical topics across TG-02 to TG-05 - Identify which decisions need two sessions (prepare→conclude) | - Endorse WP plan; confirm all lead authors (BM-03 needs volunteer) - Agree topic schedule TG-02 through TG-05 — frames all subsequent work | Chair circulates: BM-01 draft, BM-02 draft, WP plan, Carruthers roadmap summary, proposed topic allocation. All ≥5 working days before. | BM-01 BM-02 Plan doc |
| TG-02 — 9 Apr 2026 15:00 CEST |  |  |  |  |  |
| 2 | 9 Apr 2026 15:00 CEST | - Selectivity: block-based alternatives (BM-01 §6.1) vs time-varying; fleet implications - Reference points: fixed RPs vs dynamic BMSY/FMSY — pros, cons, RFMO precedent - S-R alternatives: simplified options (single BH, regime variants) from BM-01 §6.2 — initial reaction - Indices (BM-03): inventory of all 7, CPUE standardisation, index–biomass proportionality - Uncertainty dimensions most consequential for long-term projections | - Discuss selectivity block options — narrow to ≤2 candidates (conclude TG-03) - Discuss reference point approach — identify preferred direction (conclude TG-03) - Confirm BM-03 lead and scope; agree index standardisation methodology | BM-01 §6.1–6.3 fitted diagnostics; BM-03 outline; updated topic schedule from TG-01 | BM-01 BM-03 |
| TG-03 — 30 Apr 2026 15:00 CEST |  |  |  |  |  |
| 3 | 30 Apr 2026 15:00 CEST | - CONCLUDE selectivity: agree block structure(s) for OM conditioning - CONCLUDE reference points: agree fixed benchmark RPs; document rationale - Far North treatment (BM-01 §6.4): options for h1/h2 consistency - OM grid design (BM-04): reference set vs robustness set; which uncertainty axes in each tier - Benchmark handoff: define minimum outputs needed for TG-04 to proceed | - Agree selectivity block structure for OM (carried from TG-02) - Agree fixed reference point approach (carried from TG-02) - Agree harmonised Far North treatment for both stock hypotheses - Agree OM grid structure: axes, tiers (reference set vs robustness set) - Agree criteria for OM reconditioning decision at TG-04 | BM-01 §6.4 draft; BM-03 first full draft; BM-04 outline with OM grid sketch; Chair circulates 'Benchmark handoff checklist' | BM-01 BM-03 BM-04 |
| TG-04 — 28 May 2026 15:00 CEST |  |  |  |  |  |
| 4 | 28 May 2026 15:00 CEST | - Lima Benchmark debrief: model simplification, indices, OM design — what was agreed and what remains open - CRITICAL FORK: Recondition on Benchmark OM outputs OR proceed with SC13-based OM - Stock-hypothesis: using base case + robustness tests to derive advice; attempt consensus - Performance metrics (MSE-02): conservation (P(B<BLIM), P(B<BMSY)), yield (avg catch, AAV), stability metrics - MP families: candidate model-free (DLMtool) and model-based (multi-index, surplus production) | - CRITICAL: Recondition OM on Benchmark outputs OR proceed with SC13-based OM — gates Wageningen scope - Agree S-R priors (steepness, σR) and recruitment regime treatment across all OMs - Discuss stock-hypothesis treatment for advice — to conclude at TG-05 - Endorse draft performance metrics and time horizons (5/10/20+ yr) — to finalise at TG-05 | Lima Benchmark summary circulated after meeting; BM MSE-02 draft performance metrics | BM-04 MSE-02 BM-01 outcomes |
| TG-05 — 11 Jun 2026 15:00 CEST |  |  |  |  |  |
| 5 | 11 Jun 2026 15:00 CEST | - CONCLUDE stock-hypothesis: close from TG-04 (or confirm fallback) - CONCLUDE performance metrics: finalise metric list, time horizons, risk tolerance for Wageningen - MP specifications (MSE-01): technical freeze — data streams, tuning targets, HCR, Buffer/K60 - Robustness scenario matrix: finalise all scenarios entering Wageningen (MSE-03) - Cross-platform validation: FLR vs RTMB/OpenMSE — metrics, responsibilities (WMR/CHL/PER), timeline - Wageningen logistics: trade-off format (Slick, worm plots, Kobe-style); decision-making protocol | - Conclude stock-hypothesis (from TG-04) - Finalise performance metrics list, time horizons and risk tolerance - Freeze MP specifications: no new MPs added after this TG - Agree complete robustness scenario matrix (reference set + robustness set) - Agree cross-platform validation protocol and assign responsibilities - Agree Wageningen communication and decision-making format | Full drafts MSE-01 and MSE-03; Slick/trade-off prototype if available; updated OM status note from WMR | MSE-01 MSE-02 MSE-03 |

Notes: (1) If Lima Benchmark endorses reconditioning the OM, TG-04 agenda must adjust to incorporate benchmark outcomes before Wageningen. (2) The stock-hypothesis weighting decision (TG-04) is a potential sticking point — plan extra time or a dedicated sub-group call if no consensus at TG-03. (3) All working paper drafts should be circulated at least 5 working days before each TG.